## Strategy
[12 empty] | B | R | A | G
KPI’s | Strategy Objective | Key Milestones | Accountable Lead | Collaborators | notes | Q4 update (Jan - Mar 2023) | Q1 update (Apr-June 2023) | BRAG | Q2 Update (July to September 2023) | Q3 Update (Octboer to December 2023) | Q4 (December to end of March) |  | Not Achieved | Risks Slippage | Completed
1.1 | 1. The board (non-exec and exec members) endorses the violence prevention and reduction policy | PMVA Strategy meets legislative and board requirements | MVAC Chair |  | Monitor trust PMVA plan at MVAC meetings every 6 week until compliance is achieved. | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months | As at Q4. People Committee receiving an update on 27th July |  | As at Q1. People Committee receiving an update on 27th July | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, next update into People Committee on 26th January 2024 | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, last update went in January 2024
1.2 |  | Strategy has been assessed against policy and risk assessments | MVAC Chair
1.3 |  | Strategy agreed with unions, H&S representatives and relevant stakeholders | MVAC Chair
1.5 |  | Documentation clearly states Chief exec & board is accountable for PMVA strategy & policy | MVAC Chair
1.6 |  | Analysis to assess PMVA disparity from groups with protected characteristics - Full equality impact assessment developed and circulated to ALL stakeholders | MVAC Chair | Link to 9.3
2.1 | 2. Clearly defined objectives and performance criteria | PMVA objectives & performance criteria incorporated into policy | MVAC Chair |  | Objectives & performance criteria set out in people strategy | Revised policy should come through MVAC for endorsment. Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months | As at Q4. People Cpmmittee receiving an update on 27th July |  | As at Q1. People Committee receiving an update on 27th July | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, next update into People Committee on 26th January 2024 | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, last update went in January 2024
2.2 |  | Measures have been set for objectives against compliance criteria | MVAC Chair |  | We currently measure V&A through conflict score card
2.3 |  | Compliance criteria met for H&S & statutory legislation - Validated by organisation auditors | MVAC Chair
|  | Address disparity in skills for staff with protected characteristics - Referenced in equality impact assessment | MVAC Chair |  | EIA is completed for all policies to address this
3.1 | 3. Violence prevention and reduction plans recorded, implemented and maintained | Action plan developed and documented for PMVA - Objectives and outcomes set out in policy | MVAC Chair |  | Set out in people strategy | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months | As at Q4. People Cpmmittee receiving an update on 27th July |  | As at Q1. People Committee receiving an update on 27th July | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, next update into People Committee on 26th January 2024 | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, last update went in January 2024
3.2 |  | Schedule for updating documents created (min 12 month) - improvements, lessons learnt, risk assessments implemented | MVAC Chair
4.1 | 4. Board members approve resource | Senior managers ensure required resources are provided to meet PMVA objectives | MVAC Chair | Check the resources are available to meet the PMVA objectives set out in the people strategy |  | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months | As at Q4. People Cpmmittee receiving an update on 27th July |  | As at Q1. People Committee receiving an update on 27th July | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, next update into People Committee on 26th January 2024 | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, last update went in January 2024
4.2 |  | Director designated to manage PMVA work stream - must ensure sufficient resource provided (underpinned by risk assessment) | MVAC Chair | Assessed once plan has been completed to check resource needs and address if required.
5.3 | 5. Regular workforce engagement | Trade unions are consulted & involved in development of PMVA objectives | MVAC Chair |  |  | Unions are represented at MVAC to meet this objective | No comments to add
5.4 |  | Equality and diversity applied to objective development in line with public sector equality duty | MVAC Chair |  |  | All policy / plans developed with EIA in line with EA 2010 - new documents will need to be checked to ensure they meet this framework | No comments to add
6.1 | Roles, responsibilities & training (action update in H&S) | Roles & responsibilities across all levels set out in a PMVA policy | MVAC Chair | Meeting with HL/SC to establish a potential T&F group |  | A number of polices have been collated from other organisations and will be used to inform the development of a Trust Wide policy. The T&F group will determine the deadline for the policy | Action update in H&S section |  | Action Update in H&S section | Action in H&S section
8.2 | Process to assess violence prevention and reduction performance (action update in H&S) | Senior leaders become directly accountable for policy working and objectives of PMVA are achieved | MVAC Chair | Senior leaders to track progress against achieveing PMVA policy working to reduce V&A incidents and that objectives set out in the people strategy are achieved |  | A number of polices have been collated from other organisations and will be used to inform the development of a Trust Wide policy. The T&F group will determine the deadline for the policy | Action update in H&S section |  | Action in H&S section | Action in H&S section
12.1 | 6. Board reviews PMVA performance | Finding of 6 monthly senior manager review shared with board | MVAC Chair |  |  | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months | No comments to add |  |  | Robust governance as 6 weekly MVAC meetings chaired by deputy chief executive and escalated to people committiee and trust board every 6 months, next update into People Committee on 26th January 2024
13.1 | 7. PMVA policy updated | Following reviews in 12.1 PMVA lead updates objectives, policy, plans and processes if required | MVAC Chair | PMVA lead to ensure required changes have been made to policy, plans, process if required after 6 monthly review in 12.1 |  | A number of polices have been collated from other organisations and will be used to inform the development of a Trust Wide policy. The T&F group will determine the deadline for the policy | Action update in H&S section |  | Action in H&S section | Action in H&S section | Trust wide policy launched 18th December 2023, an amendment to one of the guidance documents to allign to RE and ISWM presented to MVAC on 18th March.

## H&S
[11 empty] | B | R | A | G
Strategy Objective | Key Milestones | Accountable Lead | notes | Collaborators | Q4 update (Jan - Mar 2023) | Q1 update (Apr-June 2023) | Q2 Update (July to September 2023) | Q3 update (Oct-Dec 2023) | Q4 update (Jan - Mar 2024) | BRAG | On Plan | Not Achieved | Risks Slippage | Completed
The board (non-exec and exec members) endorses the violence prevention and reduction policy | Risk assessments conducted and shared with ICB | H&S | Risk assessments to be shared with ICB via LH/JN. |  | The Zero Tolerance policy became obsolete in October 2022. Without access, staff are unable to access the risk assessment template | Task and finish group reviewing/developing a suitable policy based on the PVA standard. Completion anticipated by end of June 2023. Request made to reinstate the existing policy to permit access to the risk assessment template. | Draft policy now complete and circulated to MVAC membership for wider review. Also with the Policy Assurance Group for review | Prevention and Management of Violence and Aggression Policy now complete with policy launch date of December 11th by the Communications Team. | Policy complete and available on MyStaff App. Some issues ocurred in Early March with links not working during transistion from DMS however quickly fixed
Violence prevention and reduction plans recorded, implemented and maintained | Risk assessments available to managers, staff, unions any other relevant stakeholders | H&S | Completed risk assessments held at department level. No central store |  | Where completed, assessments are accessible within the local areas. This objective will be met when full coverage of risk assessments is achieved. | Annual H&S department audit requested for completion in June/July 2023. Collated returns will identify level of compliance | Collated divisional responses sent to Divisional H&S Leads 6/10/2023 for development of action plans. Monitoring of progress for compliance is via the H&S Committee. | Plans are recorded within this BRAG document and actions to address are recorded within risk 422. Ongoing procedural documents are linked within the newly developed policy | Status as of Q3 remains in place. Work continues to produce a tailored training programme for department V&A risk assessments. Dates for training now established and will commence in April 2024. Datix review of categories /sub-categories now complete with changes to commence from April 1st.
Risk assessment | PMVA Risk assessments are in place, monitored and recorded in line with policy. | H&S | Divisional risk assessments are currently held locally, these need to be returned centrally and assessed against policy |  | Risk assessments are saved locally within the departments they relate to. As a trust, we do not have a central holding area for assessments. Annual audits permit us to monitor compliance. The 2022 audit identified 35% coverage. The policy is the only link to the assessment template. As the policy is not currently available, depts are not able to access the assessment template. | We only have an annual opportunity to monitor risk assessment completion. A sharepoint could be used but ideally, would cover every type of risk assessment. | No current progress against a central store but plan to enage Digital Services for assistance with development of Teams or Sharepoint page with trustwide access and editor ability | Meeting held with Digital Services with agreement that a sharepoint site could be used to centrally store risk assessments. IT Clinical Systems Manager will provide assistance to ensure correct editor access. The newly launched policy contains an approved risk assessment template. Request to be made to divisions to complete within the next Trust H&S Committee in January 2024. The internal H&S audit from June - August 2023 identified 48% compliance for completion of risk assessments | Progress to find a solution for a central storage for risk assessments ongoing. Possibilities within Datix modules being considered. If not possible then a SharePoint storage site will be considered however recognised that version control could be an issue. In any event, risk assessments are completed and held within local departments so compliance with risk assessment completion will address this requirement.
| Known risks understood across organisation. Stakeholders and senior managers aware of these | H&S | Key risks to be communicated to stakeholders and senior managers from returned risk assessments in 7.1 |  | A trustwide risk exists at a coroprate level. Risk 422 is updated/raised within the People Committee. Department or divisional risks are also entered onto the risk register. Trustwide awareness of the extent of incidents within this category is covered within quarterly and annual reports. The percentage of V&A incidents within totals of annual incidents within H&S categories is covered within Managers H&S training | Risk 2532 / 5320 / 422 all monitored within the People Committee. | Some reduction of incidents noted. It Stops with Me campaign launched in Oct plus review of incident categories with Datix envisaged to assist towards a clearer understanding of incident causation and assist with identification of further controls | It Stops with me campaign in place. Review of incident categories agreed but awaiting the end of the year to go live with changes in Datix to ensure no disruption of extractions required for annual reports. Change anticipated for April 1st 2024. Corporate Risk 422 updated within Q3. | Risk 2532 / 5320 / 422 all monitored within the People Committee. 5320 relates to lack of training resources. No current actions identified and last updated 18/12/23. Score of 8. Risk 2532 relates to low volume of clinical holding/restraint training results in non- compliance of CQC Reg (13). Current score of 9. Last reviewed on 18/12/23 with no outstanding actions. Risk 422 is a corporate risk that patients and staff will experience violent or aggressive behaviour. Current risk score of 12 with target of 6 to be achieved by September 2024. 3 outstanding actions to achieve a reduction of incidents
| Known risks understood by staff. Control measures communicated to all staff in regular updates | H&S | Plan to inform staff of key risks and how to deal with them in regular updates (comms/connect/training/team meetings) |  | Conflict Resolution training available as part of the 11 core mandatory topics. Compliance as at March 2023 was 93% trustwide. Other local communication routes exist at local level for sharing feedback and learning from incidents |  | Maybo training now commenced | Intention to commence Risk Assessment training specifically for violence and aggression. Programme content to be developed with Corporate Trainer | Training dates identified to commence risk assessment training in April 2024. Maybo training in place
Process to assess violence prevention and reduction performance | PMVA process & plans assessed and reviewed every 6 months or following major change or incident | H&S | Assess incidents against policy and process followed - if findings show need review and revise policy |  | Progress against this should be tracked as an agenda item within the PMVA Committee focussing on main incident themes. No current policy in place to assess against | No change | Policy now in place undergoing final review. Ongoing monitoring of incidents can be assessed against policy processes | Incident reduction features within Safety Dept objectives with an amitious 10% reduction aim. Scorecard tracker in place with 1/4 review within the Management of Violence and Agression Committee (MVAC). Some reduction to physical assualts noted since commencement of Violence Reduction Officers | Increasing number of cases brought to the criminal justice system with support from VRO's. Reduction of violent incidents still reducing. Ongoing reduction of physical assault incidents
| Organisation encourage and promotes staff to report all incidents & near misses | H&S | Ensure multiple lines of communication set up to encourage staff to report incidents on datix |  | We have always encouraged incidents to be reported however it is recognised that it is a 'subjective' topic and not every incident will be entered. Opportunities exist to record and enter multiple incidents in high risk areas due to time capacities |  | It Stops With Me campaign now live should assist in promoting reporting of incidents | Ongoing promotion to report incidents. No reason to suspect incidents are not reported | All incidents encouraged to be reported in Datix however accepted that the topic can be 'subjective' with individuals. Changes to the Datix reporting system are designed to streamline reporting and focus on learning
Data is traceable, retrievable & accessible | Incident reports managed in line with GDPR | H&S |  |  | Managed via Datix User Group, Datix Governance Group, Trust Risk Manager, Safeguarding, GDPR Lead, Datix Administrator
Process for corrective and preventative actions for PMVA | All incidents logged, reviewed, corrective actions taken and recorded. If delayed by investigations/staff support must be communicated to senior management, relevant staff and stakeholders | H&S | ensure this criteria is converted into part of the incident follow up procedure (VSO's)? |  | Sopportive offerings include Trauma Counselling, OH support, 1:1's, Victim Support Officers
| PMVA risk registers are updated accordingly in event of learnings | H&S | In the event of learnings, risk assessments to be updated - record of ammends logged on version control | should this be within the security section? | Risk Management policy covers this requirement. Risk Register prompt for review. Serious Incident policy in place. Serious incidents are fully investigated and learning shared

## Comms
[12 empty] | B | R | A | G
Strategy Objective | Key Milestones | Accountable Lead | Notes | Collaborators | Q4 update (Jan - Mar 2023) | Q1 update (Apr - Jun 2023) | Q2 update (Jul - Sept 2023) | Q3 update (Oct - Dec 2023) | Q4 update (Jan - Mar 2024) | Q1 update (Apr - Jul) | BRAG | On Plan | Not Achieved | Risks Slippage | Completed
Regular workforce engagement | Regular accessible communication schedule implemented on PMVA objectives and priorities | Comms | mini site on connect & other communication streams |  | Communications objectives drafted to discuss with MVAC on 24 April. Once objectives are agreed, strategy and implementation plan can be developed which will require input from and support for delivery by MVAC members | Feedback received on comms objectives. Used to develop strategy for discussion at MVAC. When strategy is agreed, communications implementation plan will be developed that will signal the start of the delivery of communications. | Implementation plan updated. Creative approved and in use for It Stops with Me. Met with xxxxxx re: data publication In communication withVRT re: successful prosecutions. It Stops with me campaign launched 11 Sept | Communications schedule in place with activity planned until January 2023 including: RE approach launch (internal) MVAC data publication (external) New V&A policy launched (internal) | Communications schedule in place with activity planned until July 2024. | Communications schedule in place with activity planned until July 2024. Some delays dependent on new Trust brand and cultural transformation plans | B
| Communications sent to all staff groups and functions across organisation | Comms |  |  | Content for communications to be shared and discussed at MVAC meetings | Comms this Q: Media statement about V&A stats following Open Board, coverage on BBC online and Bristol Live Next planned comms: Change to VSO name Recruitment to mediation training | Follow up mediation training comms issued. Promotion of RE workshops ongoing ISWM posters / collateral in development Planning for BHM in October | ISWM BH month activity included Newsbeat feature and presentation at event (cancelled due to overrun of event) Additional activity re: sexual assault and harassment delivered following Working Party on Sexual Misconduct in Surgery published report including Divisional cascade and new content for ISWM connect page Presented campaign overview to Division of Medicine V&A group. During Anti-bullying week (November) we supported the People team to launch their new Respecting Everyone framework, including it in Newsbeat in xxxxxx intro, linking to the new SharePoint site from communication content and a new intranet homepage tile, sending an all-staff email from xxxxxxx as a call to action and sharing a divisional cascade message signposting managers to the new resources available. ISWM posters finalised and shared with MVAC members to coordinate local distribution. Published Q1 and 2 V&A stats in system-wide story. Included internal comms to colleagues ahead of publication, social media and a press release. Publicised the new V&A policy internally. Intranet traffic increased by 1120% from 80 hits in August before the campaign launched to 603 in September and 976 in October demonstrating the effectiveness of the campaign in driving behaviour change in staff and encouraging action. | xxxxxx interviewed for BBC Points West - coverage as lead story on lunchtime and evening news on Thursday 4 Jan. Supported LGBT+ history month plans through internal comms channels. Drafted xxxxxx IWD message to include links to RE and ISWM. Planning for sexual safety focus comms - considering new Trust brand and channels, sexual safety charter, staff survey results. Prepared session on cultural transformation / Trust brand for People Committee. Planning for change in Datix recording comms. Researched and drafted Activity Coordinator case study. With xxxxxxx for review. | Finalised Activity Coordinator case study - to discuss with MVAC members best way to share. Planning cultural transformation wortk (full-hearted care) that will support MVAC messaging. | B

## Education
[12 empty] | B | R | A | G
Strategy Objective | Key Milestones | Accountable Lead | Notes | Collaborators | Q4 update (Jan - Mar 2023) | Q1 update (Apr-June 2023) | Q2 update (July-Sept 2023) | Q3 update (Oct - Dec 2023) | Q4 update (Jan - March 2024) | BRAG | Q1 update (Apr-June 2024) | On Plan | Not Achieved | Risks Slippage | Completed
Violence prevention and reduction plans recorded, implemented and maintained | Consultation of plans with SME's pertaining to Equality Act 2010 | Education | Education SME's involved in consultation of plans | OD |  | The milestone sits across areas and is linked to the roll-out of a more consistent audit process and governance which is in a developmental stage | As Q1 | Draft paper to be presented to MVAC on the 9th January proposing an audit group to review indicents within the Trust and lessons learnt. The remit of the audit group will address many of the points linked to this milestone. | Incident audit review group established and reviewing incidents recorded to Datix.
Roles, responsibilities & training | TNA based on risk assessment undertaken - suitable training provided to all staff | Education | Maybo TNA is risk assessment based, currently in progress to assess staff training needs. |  | Two trainers have completed the Maybo training to enable the delivery of the reduction and restraint of violence. A schedule of training to be developed to roll out across the divisions. | Four members of staff have completed the Maybo training. We are currently reviewing the requirements of the Maybo restraint provision and how that can be dovetailed to the risk audit. | Training is commencing following the completion of the training programme - proposed paper is brought to MVAC | Training schedule for 2024 released to divisions with the subject lead targeting key areas in the first instance. | List of 2024 dates available for Weston & Bristol. 3 pathways available (Adults, Care of elderly, Children) Working with service leads to book staff and determine training requirement on each pathway. Staff would need to attend the modules relevant for their job role i.e. if clinical holding needed must attend 1-6. If only defensive skills needed can attend 1-3.
Board reviews PMVA performance | Input to the review must include following points; See Comment | Education |  |  | All data reported to board in line with schedule exception of ICB which will commence May 2023 | As mentioned above there is a link between the standard and the Maybo provision which could propose a sub-group to review incident reports | As above | Draft paper to be presented to MVAC on the 9th January proposing an audit group to review indicents within the Trust and lessons learnt. The remit of the audit group will address many of the points linked to this milestone. | Incident audit review group established and reviewing incidents recorded to Datix. Looking to undertake benchmarking for this with NBT who run a similar program through ICB group
Informed decisions at senior manager level | PMVA forms part of overall strategy and planning - must be aligned to ICB planning | Education | PMVA in people strategy - check if in line with ICB planning |  | ICB Academy is realigning the reporting of sub-groups, passporting and LMS group will morph into an essential training group which will include PMVA and violence reduction standard chaired by JN | The terms of reference for the LMS and passporting group have been amended and approved by the learning academy with violence and aggression added to the terms of reference. Date agreed to pull system partners together to review violence and aggression provision together | First meeting of ICB violence and aggression leads convened and welcomed by ICB partners. Draft terms of reference presented to the learning academy and future meeting date agreed. FUture activity to scope violence and aggression delivery across the ICB. | Systems Group reports to the ICB Learning and Leadership Academy provides an oversight training across BNSSG partners. The group has established a sub-group which has convened several times to review violence and aggression training across partner organisations. | PMVA system sub-group and reporting to the Learning Academy (via the System Learning Group). Group has met twice and currently scoping activity across partners organisations.

## Security
[11 empty] | B | R | A | G
Strategy Objective | Key Milestones | Accountable Lead | Notes | Collaborators | Q4 update (Jan - Mar 2023) | Q1 update (Apr-June 2023) | Q2 update (Jul - Sept 2023) | Q3 update (Oct-Dec 2023) | Q4 update (Jan-Mar 2024) | Q1 update (Apr-Jun 2024) | BRAG | Not Achieved | Risks Slippage | Completed
Informed decisions at senior manager level | Staff receive timely incident reports to incident investigations - if delayed by process this is communicated to those involved | Security | VSO's / LH to ensure incident reports are timley or communicate delays | Ian Pidgen | The Victim Support Team are managed by the security Team The victim support team review all violence and aggression reports daily. The VSO Team then report this to the E&F MVAC monthly. | The Victim Support Team have been Rebranded to become the Violence Reduction Team. It is recognised that there is still some reluctance from staff to support prosecutions based on previous negative experiences with reporting incidents to the police. Comms will be supporting the messaging on this change to win the hearts and minds of staff and that the new processes adopted by the Violence Reduction Team will make the whole process much easier and user friendly. | Violence Reduction Team Court Results are now filtering through the criminal Justice System. More to infomation to follow. There is still a element of some staff unwilling to make statements and support a police prosecution. This is being addressed on a case by case basis. The Violence Reduction Officers are working hard to provide reassurance and support to encourage witnesses/victims to make statements. | Following a period of review by new Security Manager xxxxxx, and further clarification receieved from MVAC as to the role and responsibilities of the VRO's, I can confirm all incidents of V&A reported will be addressed and lines of support provided. In order to achieve meaningful and clear data, all VRO action and engagement will be recorded and managed on internal databases. Measuring efficacy of the VRO efforts will be via prosecutions achieved, total engagements, satisfaction surveys and intended reduction in incidents of violence trust wide. There is recruitment underway to obtain further resource for the VRO Team and ensure the needs of the staff, MVAC and Trust are met. **Update 05/01/2024 - Recruitment of additional VRO completed starting with us on 29/01/2024 | I can confirm all incidents of V&A reported will be addressed and lines of support provided. We have an additional member to the VRO team who is steadily getting up to speed with our processes, training and orienteering. Update 25/03/2024 - Revision of service provided to a risk based approach to enable the most serious of incidents to be prioritised. VRO compliment has reduced due to resignation. VRO permanent role is being pushed for banding confirmation to enable stability and full time resourcing to be achieved. 13/05/2024 - Interviews being scheduled for Full Time Permanent VRO. Appointment likely to be occuring July time. Onboarding and project review underway to determine achievable development of support to be provided and identification of prevention methods and teaching points post incident. Flagging with MVAC : absences sheduled during June which will reduce support available. | I can confirm all incidents of V&A reported will be addressed and lines of support provided. We interviewing for an additional member to the VRO team 31/5/24 - Revision of service provided to a risk based approach to enable the most serious of incidents to be prioritised. VRO compliment has reduced due to resignation. VRO permanent role has been banded to enable stability and full time resourcing to be achieved post 31/5/24. Really good pool of candidates - Appointment likely to be occuring July time. Reduct service provision 3-17 June due to annual leave, datix will still be reviewed and monitored. Onboarding and project review underway to determine achievable development of support to be provided and identification of prevention methods and teaching points post incident. Flagging with MVAC : absences sheduled during June which will reduce support available. | B

## Divisions
[67 empty] | B | R | A | G
KPI’s | Strategy Objective | Key Milestones | Accountable Lead | Notes | Collaborators | Medicine Q4 update (Jan - Mar 2023) | Medicine Q1 update (Apr - June 2023) | Medicine Q2 update (July - Sept 2023) | Medicine Q3 update (Oct - Dec 2023) | Medicine Q4 update (Dec 2023 - March 2024) | Medicine Q1 Apr - Jun 2024 | BRAG | W&C Q4 update (Jan - Mar 2023) | W&C Q1 update (Apr - June 2023) | Women's Q2 update (July - Sept 2023) | Women's Q3 update update (Oct - Dec 2023) | Women's Q4 update (Dec 2023 - March 2024) | Women's Q1 Apr - Jun 2024 | BRAG | Children's Q2 update (July - Sept 2023) | Children's Q3 update update (Oct - Dec 2023) | Children's Q4 update (Dec 2023 - March 2024) | Children's Q1 Apr - Jun 2024 | BRAG | Surgery Q4 update (Jan - Mar 2023) | Surgery Q1 update (Apr - June 2023) | Surgery Q2 update (July - Sept 2023) | Surgery Q3 update update (Oct - Dec 2023) | Surgery Q4 update (Dec 2023 - March 2024) | Surgery Q1 Apr - Jun 2024 | BRAG | D&T Q4 update (Jan - Mar 2023) | D&T Q1 update (Apr - June 2023) | D&T Q2 update (July - Sept 2023) | D&T Q3 update update (Oct - Dec 2023)) | D&T Q4 update (Dec 2023 - March 2024) | D&T Q1 Apr - Jun 2024 | BRAG | Specialised Services Q4 update (Jan - Mar 2023) | Specialised Services Q1 update (Apr - June 2023) | Specialised Services Q2 update (July - Sept 2023) | Specialised Services Q3 update update (Oct - Dec 2023) | Specialised Services Q4 update (Dec 2023 - March 2024) | Specialised Services Q1 Apr - Jun 2024 | BRAG | Weston Hospital Q4 update (Jan - Mar 2023) | Weston Hospital Q1 update (Apr - June 2023) | Weston Q2 update (July - Sept 2023) | Weston Q3 update update (Oct - Dec 2023) | Weston Q4 update (Dec 2023 - March 2024) | Weston Q1 Apr - Jun 2024 | BRAG | Trust Services Q4 update (Jan - Mar 2023) | Trust Services Q1 update (Apr - June 2023) | Trust Services Q2 update (July - Sept 2023) | Trust Services Q3 update update (Oct - Dec 2023) | Trust Services Q4 update (Dec 2023 - March 2024) | Trust Services Q1 Apr - Jun 2024 | BRAG | E&F Q4 update (Jan - Mar 2023) | E&F Q1 update (Apr - June 2023) | E&F Q2 update (July - Sept 2023) | E&F Q3 update update (Oct - Dec 2023) | E&F Q4 update (Dec 2023 - March 2024) | E&F Q1 Apr - Jun 2024 | BRAG | On Plan | Not Achieved | Risks Slippage | Completed
9.2 | Data is traceable, retrievable & accessible | Incident reports analysed to support audit process and inform ongoing strategy | Divisions | Link to 3.1 - 10.1 - 13.1 - 14.1 - divisional template to address these criteria - standing item at MVAC |  |  |  | Data collected using datix and dashboard. learning shared as part of safety briefs, themeatic learning and as part of staff story to divisional board. | high numbers of V&A reported in september and december - of which highest proportion reported from the AED. when reviewing the datix in last 2 years similar patterns but no themes. . | QPST continue to monitor and report divisionally incidents including trends. this is shared at the divisional governance committee. |  |  | Childrens Update: Datix Dashboard with x5 Risks and All datix incident reports, reviewed monthly, with a process to be identified to analysis themes. | Childrens Update: Dashboard reviewed monthly, with furhter breakdown & theme analysis, feeding into H&S forum. | All data is traceable via Datix reports. It is accessible for all staff with access to Datix to review. | Datix reviewed for this quarter. Limited access to Datix for all areas of Women's . Awaiting additional access | Access now to Datix for Women. |  | G | Dashboard contiuned to be reviewed monthly to analyse themes - with hot spots exception reported | Same as Q2 | Divisional dashboard - incident reports analaysed & reviewed monthly jointly with H&S lead. |  | G | Incident dashboard now in place and to be reviewed monthly. Ongoing work to develop a sustainable process to review themes. | Dashboard reviewed monthly. | Dashboard continues to be reviewed monthy. Patient safety team also prepare departmental incident reports for discussion at specialty governance meetings. | Incidents continue to be analysed regularly across the division. Dashboard continues to be reviewed and the patient safety team's departmental incident reports are presented at specialty governance meetings. | As Q3 41% reduction of incidents Jan vs Dec. 16 reported incidents in Feb and an increase to 21 in March . Loking at how we feed this information into team meetings across division. |  | B | Governance Manager continues to review all incidents on a daily basis and action any moderate and above. Service/Governance Leads also review on daily basis and assign handlers. Incidents are then investigated and actioned as appropriate. | Incidents reviewed regularly and then investigated and actioned as appropriate. | Incidents reviewed regularly and then investigated and actioned as appropriate. A new Patient Safety Coordinator is supporting the division to cover sickness absence. | Incidents reviewed regularly and then investigated and actioned as appropriate. | Incidents reviewed regularly and then investigated and actioned as appropriate. D&T staff survey results tell us that 6.4% of staff (52 people) have experienced physical violence/ abuse from patients/ service users but only 55.6% of them (30 people) reported it. We had 12 incidents recorded on Datix during this time. Suggests under reporting. Held awareness raising meeting in April to encourage recording. Suggested further evidence of incidents not being reported. Impact in terms of incidents recorded expected in Q1 24/25 onwards. Following up additional session in Audiology to target clinical staff |  |  | All incidents reviewed daily/ real time. all incidents are assigned a handler on review. Actions arise depending on the required response. | Nil new to update. | As Q4, however, need to await outcome of SBAR review at Oct meeting. | Nil moderate harm incidents in Q3 Increase on V&A in Q3 (note: abuse patient to staff 7x Q2 / 10x Q3) All incidents reviewed daily, wiht approprate handler. Actions dependant on required response | Increase in icident records again this quarter, 52% verbal abuse by pateitn to staff, 10%staff to staff. 24% physical abuse patients to satff and 10 racial abuse by patients to staff action tracker now in place to ensure that we follow up all incidents int the divisn and provide support. |  | B |  | Dashboard has been set up. All V&A incidents are managed by the Patient Safety Team and assigned as appropriate. Trends, numbers of incidents and new actions to be reported through Clnical Quality Committee via Patient Safety Team monthly report. | Nothing new to update | Dashboard in place, regular incident review and appropriate investigation | Dashboard in place, regular incident review and appropriate investigation | Dashboard in place, regular incident review and appropriate investigation. Will also begin to report through the Weston People Committee going forward as V&A is a focus of the Culture and People Plan. | B | [7 empty] | The victim support team review all violence and aggression reports daily. | No change from last quarter The victim support team review all violence and aggression reports daily. | No change from last quarter The victim support team review all violence and aggression reports daily. | Datix reviewed daily by the Security Manager. | Data reviewed daily by Security Manager and then proritised out to the VROs | Data reviewed daily by Security Manager and then proritised out to the VROs | G
9.3 | Data is traceable, retrievable & accessible | Data analysed and categorised based on demographic make-up of workforce categorised by protected characteristics | Divisions | analysis needs to be done, finding of this fed back to understand impact |  |  |  | dashboard up to date. only currently recording racial abuse, have requested to add other demographics | Racial and homophobic abuse reported from list of protected charateritics. | Staff are reporting racial/homophobic/mosgynistic abuse, which is regularly datixed. |  |  | Childrens Update: Demographic detail - understanding of how currently captured within incident reports required inorder to progress this. Data analysis scheduled for monthly inorder to them inform divisional workprogramme. | Childrens Update: If demographic info included incident report, reviewed within analysis & themes - with which to inform divisional workprogramme. | This is not routinely undertaken, unless gender / race is a specific factor of the incident. | As per Q2 | As per Q3 - no change. |  | A | Same as Q1 | Same as Q2 | Data - demographics analaysed with detail that is reported within incidents. |  | A | Understanding how the demographic data of the staff (involved in the incident) is captured to be able to progress this action. | Incidents are grouped and themed in order to identify areas for improvement. | Demographic data of staff involved is not routinely captured and responded too. Support required for this. | As Q2. | No change to Q2 - how to review with demographic detail TBC. Meeting with governance team to try to produce individual department trends so share with managers |  | R | Services within D&T follow the PMVA trust guidance. Incidents are grouped and themed to identify areas for improvement. In Q4 there were four incidents involving violence and aggression. 3 of these involved the same patient and same event. Fourth incident involved verbal abuse between staff members which has been managed and closed. | Incidents continue to be grouped and themed to identify areas for improvement. In Q1 there were three incidents involving violence and aggression. | Incidents continue to be grouped and themed to identify areas for improvement. In Q2 there were four incidents recorded under the Health and Safety Violence and aggression category. Of the four incidents, three were recorded as negligible harm and one as no harm. |  | Challenge to effectively categorise due to the number of incidents currently reported. |  |  | Demographic data of staff involved is not routinley captured and responded too. Support required for this. | As Q1 |  |  | No progress on this to date. |  | R |  | Support is required for the identification of demogrpahic data of staff. | Support is required for the identification of demographic data of staff. |  |  |  | R | [7 empty] | The VSO Team then report to the security management team and also to the E&F MVAC monthly. The reports and investigations are recorded on Datix and the Victim Support Officer case files | No change from last quarter | No change from last quarter | No change from last quarter | No Change from last quarter | No Change from last quarter | G
9.5 |  | Data analysed should show process are effective, identify areas for improvement and policy is achieved | Divisions | Schedule set for analysis of data against policy and areas for improvement implimented |  |  |  |  | Education and training commenced and prioritised. Piece of work starting in ED, around length of time and cost to be compliant with trust training | monitoring of risks continue. Wellbeing support being offered. we are able to see that though the incdients of V&A are not neccesarily reducing, the retention and turnover of nursing staff is greatly reduced and part of this will be the weel bineg offer and how we support staff post incident |  |  |  |  | This is not routinely undertaken, unless gender / race is a specific factor of the incident. Due to low volume of reported incidents, no current themes . | As per Q2 | Now improved access - will be able to assess if any areas for improvement. |  |  | SAme as Q1 | As Q2 | Themes if identified are propsed to be added to programme of work for divisional MVAC responsivenss |  |  |  |  | Incidents continue to be grouped and themed in order to identify areas for improvement. | Incidents continue to be grouped and themed in order to identify areas for improvement. | Incidents continue to be grouped and themed in order to identify areas for improvement. | [5 empty] | Incidents continue to be grouped and themed to identify areas for improvement. | Line manager guidance on how to support staff and implement policy being developed to support this analysis. |  |  |  |  | As Q1 | As Q1, although staff survey may be able to a support to some extent | tracker allows for thematic review. Discussed in H+S forum quartely for learning and improvement. | [5 empty] | Incidents continue to be grouped and themed to identify areas for improvement. | There has been one incident of Moderate harm which is currently under investigation as only happened on 18th March
10.1 | Established audit and assurance process for violence prevention and reduction | Process created to audit PMVA. Associated systems effectively managed and regularly assessed | Divisions | Process set out to audit PMVA - schedule assessment frequency |  |  |  | Medicine is supported of the SBAR and recommendations | Medicine have reported 1 incidnet of moderate harm, which had an RIR. learning was around Parva spray and the care of patients exposed and also about when to call on-call consultant | Recent attendance at review of incident - audit. learning shared with unit and woder within the division (learning was around allocation of ECO care and around de-escaaltion of aggressive behaviour) |  |  | Childrens Update: Requesting guidance to develop audit. | As Q4 | No current audit in place. Guidance would be appreciated. | As per Q2 | No audit undertaken |  | R | Pending guidance & direction from MVAC re audit. | As Q2 | Pending MVAC audit detail whilst in parallel determining process with H&S lead |  | A | Request for support to be able to undertake this. | Quarterly divisional Health & Safety forum to be reinstated by MVAC rep who is also rep for H&S. Division represent Trust Health & Safety Committee to report by exception. | As Q1 | As Q2, and MVAC themes to be discussed at divisional sisters meeting 09/01/24. | AGM attended Sisters meeting to talk about MVAC work and role of div leads at the start of Jan. looking at whether we can introduce violence reduction champions in key areas espcially those with off sitre working such as Southmead HC Dental services. |  | A | Monthly divisional Patient Safety and Risk meeting and a quarterly divisional Health & Safety forum. Also attend Trust Health & Safety Committee to report by exception. | Monthly divisional Patient Safety and Risk meeting and a quarterly divisional Health & Safety forum. Also attend Trust Health & Safety Committee to report by exception. | Monthly divisional Patient Safety and Risk meeting and a quarterly divisional Health & Safety forum. Exploring PMVA training for those working out of hours/in remote areas of Radiology following incidents towards Radiographers/Radiography Assistants. (Will be seeking advice from Education team on Training availability and possibility of dedicated training sessions) | Monthly divisional Patient Safety and Risk meeting and a quarterly divisional Health & Safety forum. Also attend Trust Health & Safety Committee to report by exception. | Reviewing divisional structure to ensure effectively managing through H&S forum, patient safety and risk meeting and at service level. |  |  | Also request support to complete audit. however incident data and MVAC outputs shared at H+S committee, workforce committee for learning and action planning. | As Q1, key action required to develop an audit template |  |  | As above report received and reviewed at H+S committee quarterly |  | A |  | Guidance and support required to develop and undertake an audit | Guidance still required to develop and undertake an audit | Ward/department leads have been asked to identify those staff groups who will benefit from Maybo training. Close working with H&S Lead to ensure MVAC is on the agenda for H&S Forum | DDON and HRBP working to improve uptake of PMVA training | No audit currently in place, but will consider as part of CAP plan | R | [7 empty] | The victim support process is reviewed monthly by the E&F MVAC Committee A deep dive review of the process will be undertaken by the E&F MVAC committee every 6 months | No change from last quarter | No change from last quarter The victim support team review all violence and aggression reports daily. | No change from last quarter The victim support team headed up by the Security Manager, review all violence and aggression reports daily. | No change from last quarter The victim support team headed up by the Security Manager, review all violence and aggression reports daily. | No change from last quarter The victim support team headed up by the Security Manager, review all violence and aggression reports daily. | G
10.2 |  | Review held every 6 months on PMVA audit outcomes by senior managers | Divisions | Divisional senior leaders to review audit outcomes every 6 months (possibly through MVAC) |  |  |  |  | RIR reported as per process | N/A | [5 empty] | As per Q2 | V&A incidents discussed at Divisiona;l H&S Meetings. |  |  | Pending guidance & direction from MVAC re audit. | As Q2 | closely linked with above |  |  |  |  | MVAC leads to review/request support for audit. Report to H&S and workforce committees. | As Q2. AGM and new DDON to review/agree schedule for these committees. | As Q3. | [5 empty] | Services completing the Maybo training web form to identify which training pathways staff require. Noted that AHPs, Scientific and Technical staff, and Healthcare Scientists need to be included alongside nursing and medical workforce. | Pending guidance & direction from MVAC re audit. |  |  |  |  | Continue to report via H+S forum in division, summary presented at divisional risk management board for awareness and learning. | As Q2 | outputs of H+S commiite reviewed in divsional Risk management board. | [7 empty] | Relevant staff encourgaed to book into training - would be useful to see report of training uptake vs hotspot areas. | [11 empty] | No change from last quarter | No Change from last quarter | No Change from last quarter
14.1 | Informed decisions at senior manager level | Senior managers ensure enough quantifiable data to inform ongoing policy decisions | Divisions | Link to action 3.2 & 10.1 to ensure accurate data and staff are reporting incidents - Divisions to create schedule / template for feeding back data to stakeholders in order to drive policy decisions |  |  |  | Divisional MVAC committee meet bi-monthly with division wide and an MDT approach, with strong engagement | MVAC Medicine committee contiinue to report to the workforce committee, ensuring senior managers aware of the current V&A position and ongoing projects. | Division MVAC committee continues and reports into the Workforce committee alongside weelbeing and |  |  | Childrens Update: Linked into patient safety and H&S forum to provide quarterly reporting. | Childrens Update: Developing how data feeds into H&S and divisional governance group / QAC. | Insufficient quantifiable data due to low volume of reported incidents. Individual exceptions discussed at senior manage ment level. | 6 incidents reported for Q2. 4 for Ward 73. 2 for Central Delivery Suite. 1 for Early Pregnancy Clinic. | 4 incidents reported for Q4.3 Ward 73 . 1 Main Reception |  | B | Ongoing development of data to inform information updates shared at divisional H&S & governance meetings. | As Q2 | Ongoing development of data |  | B | Establishing how this data is included in the Patient Safety and Risk Management quarterly reports. | To report business quarterly via Divisional Clinical Quality Outcome Group, with report by exception through Divisional Clinical Quality Operational Group. Division work in progress to develop a SOP for witholding treatment in outpatient settings, however as this ia a trustwide need and Medicine already have guidleines can a trustwide appraoch be adopted. | As Q1 - data is reviewed via departmental governance meetings. Escalation to clinical quality and workforce. | As Q2. | As Q3. Staff continue to be asked to report all incidents via Datix. new message for divisional safety brief for April |  | A | Data reviewed through monthly Patient Safety and Risk meetings, as well as governance manager monitoring in between. | Data reviewed through monthly Patient Safety and Risk meetings, as well as governance manager monitoring in between. | Data reviewed through monthly Patient Safety and Risk meetings, as well as patient safety coordinator monitoring in between. | Data reviewed through monthly Patient Safety and Risk meetings, as well as patient safety coordinator monitoring in between. | Encouraging recording of incidents including near misses in service in order to be able to inform decisions. |  |  | Links to H+S divsional forum and through to divsional risk commitee | As Q1 | As above | As above, agreed focus for Q4 to describe a robust consistent response to V +A incidents. Considering piloting SOP in hotspot clinical areas, supported by VRO | As above. |  | B |  | Monthly reporting into Clinical Quality Committee will ensure the Senior Management Team have relevent information to support decision making. | Monthly reporting into Clinical Quality Committee and quarterly into H&S Forum will ensure the Weston Management Team have relevent information to support decision making. | Monthly reporting into Clinical Quality Committee and quarterly into H&S Forum will ensure the Weston Management Team have relevant information to support decision making. | Monthly reporting into Clinical Quality Committee and quarterly into H&S Forum will ensure the Weston Management Team have relevant information to support decision making. | Continued reporting into H&S forum and People Committee. H&S Lead reports quarterly into Clinical Quality Committee | B | [7 empty] | The Director of E&F will receive detailed reports to inform ongoing policy decisions | No change from last quarter | No change from lasy quarter | No change over year, The Director of E&F will receive detailed reports to inform ongoing policy decisions | No change over year, The Director of E&F will receive detailed reports to inform ongoing policy decisions | No change over year, The Director of E&F will receive detailed reports to inform ongoing policy decisions | G
[6 empty] | 5th June | 29th August | 9th October | 20th November 2023 | 12th February 2024 | 13th May 2024 |  | 5th June | 29th August | 9th October |  | 12th February 2024 | 13th May 2024 |  | 9th October | 20th Nov | 12th February 2024 | 13th May 2024 |  | 5th June | 29th August | 9th October | 20th November | 12th February 2024 | 13th May 2024 |  | 5th June | 29th August | 9th October | 20th November | 12th February 2024 | 13th May 2024 |  | 5th June | 29th August | 9th October | 20th November | 12th February 2024 | 13th May 2024 |  | 5th June | 29th August | 9th October | 16th November | 8th Jan 2024/12th February / 25th March 2024 | 13th May 2024 |  | 5th June | 29th August | 9th October |  | 12th February 2024 | 13th May 2024 |  | 5th June | 29th August | 9th October | 20th November | 12th February 2024 | 13th May 2024
|  |  |  | Divisional 3 Hotspot Areas: 2023 | 1 | Top 3 hot spots for the division of medicine are ED A524 and A400. 58% of reported V&A was verbal with 32% physical. No episodes were reported aboove minimal harm. |  | PMVA training prioritised for ED/AMU/A900/C0fE wards | high numbers of V&A reported in september and october 161 - of which 46% reported from the AED. The majority (55%) of reported incidents are verbal abuse, 21% pyhysical assault - which include abject thrown at staff, staff being punched. 2 datix reported as moderate harm. as per new process RIR completed for 1 episode of moderate harm. learning from the treatment of patient and staff following parva spray deployment and when to call the on call consultant. | Verbal abuse remains highest reported catagory of V&A but we have also seen an increase in physical abuse, with incidents like punching and objects thrown at both staff and other patients. Ed continues to be higest recorder of incidents. |  |  | Demographic detail - understanding of how currently captured within incident reports required inorder to progress this. | [6 empty] | Complex long stay admisison on Apollo 35 - High reported incidents staff assault both physical & verbal. Collaberative multi agency working ongoing. Divisional Senior team updated/ Many active actions ongoing. | Quarterly review of Risks x24 for the division Across all departments, inpatient, outpatient and emergency department. • Most prevalent reported = Physical assault by patient to staff. X11 incidents = 45% total Q2 incidents Patient cohort: Mental health needs, heightened distress, Autism | No hotspot areas for key department, Reports across all departments, inpatient, outpatient and emergency department. |  |  | Higher reporting areas in BEH & BDH. Some of this data may be due to sheer volumes of patients in BEH& BDH | Hotspots are in departments that see the highest volumes: BEH/BDH. Critical care areas that have higher incidences of delerium. | As per previous quarters A604 is the main hotspot - this is linked to patient cohort/delierium | Divisional Hotspots - A602 and A60as per previous, linked to patient delerium cases. | Hotpsots STAU and BEH ED | hotspots STAU & BEH ED |  | Radiology - considering introducing a yellow/red card warning system with patients like in ED | Radiology - when transferring patients for scans. Working with divisional HR BP to implement a V&A SOP for imaging. | Radiology - three of the four incidents took place within Radiology across multiple sites. 2 incidents involved verbal abuse from patients towards staff and 1 involved physical assault from a patient towards staff. Ongoing development of local V&A SOP for Radiology, utilising existing SOP template in place for inpatient medical wards. | Radiology - one incident reported since 1st Oct involving a patient being verbally abusive towards a member of staff. Following the incident, an alert was added to care flow for possible aggression towards staff and CRIS for any future bookings within radiology. It was recorded that the incident has been added to the audit for V&A incidents in radiology. | Radiology - one incident report since 20th November involving pt being verbally abusive to staff member ahead of MRI. Security were called to resolve the situation. |  |  |  | Support to progress understanding of demographic detail remains required. | support required around demographic data. | support required around demographic data. |  |  |  | Hot spot areas according to current open incidents are ED and Steepholm Ward |  | Suport required with identification of demographic data | Suport required with identification of demographic data | Q4 2023/24 Incidents 65 reported in total - 9 remain open Largest numbers of incidents relate to: Physical assault by patient to staff (38) Verbal abuse by patient to staff (9) Hotspots overall are ED, Sandford and Draycott Hotspots for physical assault - Sandford, ED and Draycott Hotspot for verbal abuse – ED and Uphill | Q1 2024/25 incidents reported up to 9th May 30 reported so far - 13 remain open 2 of the 30 reported were reported as moderate harm - 1 is closed and has been reported to A&S Police - assault on way to work; the other is being investigated by the OPAU ward manager. Largest numbers of incidents relate to: Physical assault by patient to staff (9) Verbal abuse by patient to staff (7) Hotspots overall are ED, Cheddar, Kewstoke Hotspots for physical assault - Cheddar and Kewstoke Hotspot for verbal abuse – ED | [8 empty] | Only 1 incident involving E&F staff in last quarter which was with porters verbal abuse between staff |  | BRI Adult ED is the primary hotspot. Security Officer was kicked | We have two main hotspots, BRI Adult ED is the primary hotspot. Childrens ED is also a hotspot | We have two main hotspots, BRI Adult ED is the primary hotspot. Childrens ED is also a hotspot
[5 empty] | 2 | Work continues with SWAST to support the trust process for excluded patients. ED V&A SOP now on DMS. working with NBT to align processes. |  | high levels of verbal abuse continue with telephone abuse to our admin teams increasing. Telephone recording to be piloted in a couple of areas. | In December the division will start 'hot debrief training' | V&A from patients who have enhanced care needs continues to be recorded. There was a recent pilot of A522 in which the division employed an activity co-ordinator for 3 months, and there was a significant drop in recorded incidents of V&A. More evalutation is to be completed but the pilot was a success so the aim will be to recruit activitiy co-ordinators in 2 of our CofE wards with the aim of rolling out across all CofE wards at some ponit. |  |  | Strategy Objective 3 -- Audit -- What happening in other divisions to share learning to enable development within childrens. | [6 empty] | Strategy Objective 3 -- Audit -- What happening in other divisions to share learning to enable development within childrens. |  | Highest reporting category - Restraint, Request for dates and information for restrictive intervention / restraint to be confirmed. |  |  | One regular attender in BEH ED/OPD requiring reasonable adjustments - High Impact User Team involvement & training for staff especially A&C Update: Security measures approved, no further incidents reported for the previous regular attender. | No further hotspots identified at this time | As per previous quarters A602 is another hotspot - this is also linked to patient cohort/delierium | New hotspots: External HC dental services (Soyuthmead and Riverside) and Oral surgery. MS picking up with dental team to explore potential mitgiation.. | No incidents in former hotspots (602, 604 and externak dental HCs)in Jan. small numbers in A602 , and BDH external sites |  |  |  | Audiology - verbal abuse due to rejected referral. Careflow letter added notifying the patient their referral has been rejected and advising them to contact their GP. If the appointment is within a short period, we will call the patient. | [6 empty] | No hot spot areas identified or themes since last report. | Increase in incident recording in Q2 ? awareness. No area of particular concern. | no hot spot areas identified or themes since last report. |  |  |  | Support required with developement of an audit template - is there one already available that all Divisions could share? |  | Hot spot areas according to current open incidents are ED and Draycott Ward | 49 incidents reported in the last quarter. Almost half of the incidents came from three areas, these are: ED - 8 Draycott - 8 Sandford - 7 | 12 Feb update 40 incidents reported (14 remain open) in the last quarter. Hotspot areas (50% of total incidents reported) are: ED - 10 (6 are closed): 1 x physical assault patient to staff 1 x threatened with a weapon 6 x verbal patient to staff 1 x verbal patient to patient 1 x verbal staff to staff Draycott - 10 (7 are closed): 7 x physical assault patient to staff 2 x physical assault patient to patient 1 x verbal patient to staff | Focus on V&A being included within Culture and People plan following review of staff survery results. CAP team will support actions agreed to take forward across the site. | [8 empty] | The VRT have triaged 57 cases in last quarter 5 of which have progressed to full investigations 4 in Medicine 1 at Weston |  | WGH Secuirty Officer was threatened with a knife outside main entrance
[5 empty] | 3 | Divisional V&A group have now sign off our guidnance 'How to support staff following an epsiode of V&A' AIm to add this to DMS and share with other divisions. |  | learning from incidents continues. | to date the division have sent out 42 unacceptable behaviour letters/4 final warning letters/4 exclusion letters/4 patients arrested because of their behaviour. | PMVA training. ED doing a piece of work on how long it will take for the ED nursing team to get through this training and what impact it will have on their headroom. |  |  | Incidents reports predominately within CED. - Hot spot area. Update in progress for acutely disturbed adolescent guideline --- ABD _acute behavioral disturbance update, specific for use in CED. | [6 empty] | Throught Childrens mental health operational group - high reporting theme use of required restraint for complex & challenging eating disorders presentations - restraint reduction strategy being considered |  | Outstanding finalization of the acutely disturbed adolescent guidelines. action ourstanding is the a pharmacy stock issue. |  |  | T&O wards - accepted I/P wards with higher reporting due to patient demographics |  | BEH regular attender actions are working well - no further incidents reported, and CCTV/ security access work is pending. | CCTV now installed, care plan ion place for regular attender. | AGM and DON to review MVAC approach in early May. | [10 empty] | Noting no FUSU guardians in division. priority for next reporting period. | 1 RIDDOR incident in divsion related to H+S | focus on roll out of respecting everyone agenda. |  |  |  | Suport required with identification of demographic data |  | Support required with developement of an audit template - is there one already available that all Divisions could share? | Keen to suport ensuring that any training is prioritised in those areas identified above. | JP now attends H&S Forum with a V&A update to be cascaded through teams | CAP Team have met with VRO who is doing some training/awareness sessions with the ED team